## Root Cause Analysis Template
Root Cause Analysis Template
Details of Issue |  | Problem Description |  |  | Root Cause Identification |  |  |  | Follow-up and Review
Date | Analyst Name | Problem Statement | Incident Details | Source | Explain Cause | Corrective Actions | Deadline | Status | Describe Results | Preventative measures | Effectiveness Assessment | Additional notes
The exact date on which the incident took place. | Name of the individual or group responsible for performing the root cause analysis. | A brief and clear explanation of the issue or challenge being examined. | A detailed account of what occurred, including relevant facts such as events, location, timing, and circumstances. | Identification of where or how the issue originated. | A thorough analysis describing the underlying reasons and contributing factors that resulted in the incident. | Specific steps or actions planned or taken to resolve the issue and reduce its impact. | The expected date by which the corrective actions should be fully implemented. | The present state of the corrective actions. | A description of the results achieved after implementing the corrective actions. | Long-term measures or controls put in place to avoid recurrence of the issue. | Assessment of how successful the corrective and preventive actions have been. | Any extra information, observations, or comments not covered in the sections above.
2026-01-15 | Operations Quality Team | Delayed order processing | Multiple customer orders were processed later than expected due to system lag during peak hours. | Order management system | Insufficient server capacity during high transaction volumes. | Increased server resources and optimized database queries. | 2026-01-20 | Completed | Order processing time reduced by 35%. | Implement automated load monitoring and scaling. | Actions proved effective with no further delays reported. | Monitoring to continue for the next quarter.
2026-01-16 | IT Support Team | System outage | Internal network was unavailable for approximately two hours affecting multiple departments. | Network firewall failure | Outdated firmware caused unexpected firewall restart. | Updated firmware and rebooted network devices. | 2026-01-21 | Completed | Network stability restored. | Schedule quarterly firmware updates. | No similar outages observed since update. | Backup firewall configuration documented.
2026-01-17 | Health & Safety Officer | Minor workplace injury | Employee slipped near loading dock resulting in minor injury. | Wet floor due to cleaning activity | Warning signage was not placed after cleaning. | viewed cleaning procedures and retrained staff. | 2026-01-22 | In Progress | No further incidents reported in the area. | Mandatory use of wet floor signs during cleaning. | Preventive measures deemed effective. | Safety audit scheduled.
2026-01-18 | Customer Experience Team | Increase in customer complaints | Customers reported slow response times from support team. | Customer support process | Staff shortage during holiday period. | Added temporary support staff and adjusted shifts. | 2026-01-23 | In Progress | Response times improving steadily. | Create holiday staffing plan. | Preliminary results show positive trend. | Full review after peak season.
2026-01-19 | Production Manager | Product quality defect | Batch of products failed final quality inspection due to incorrect measurements. | Manufacturing equipment calibration | Calibration schedule was not followed. | Recalibrated equipment and reworked affected batch. | 2026-01-24 | Not Started | Product quality returned to acceptable standards. | Implement automated calibration reminders. | No repeat defects identified. | Calibration logs updated.